## Title
Group Number: 7
Project Name: Money Market
Members:
Austin Fraley
Logan Johnston
Riley Jenkins
Teh Peh
Eshwar Kanishk Kanikanti

## To Do
Index | Front | Back
1 | As an investor I want to learn about investment so that I can perform better as an investor. | Investors can seek resources about specific investment topics
1-A | As an investor I want to learn how to trade stocks so that I can buy/sell stocks | Investors can learn about trading stocks
1-B | As an investor I want to learn about what markets are | Investors can learn about what markets are
1-C | As an investor I want to learn about penny stocks so that I can make smarter descisions | Investors can learn about penny stocks
1-D | As an investor I want to learn about day trading so that I can day trade better | Investors can learn about day trading
1-E | As an investor I want to learn about long term stock investment so that I can perform better | Investors can learn about long term stock investment
1-F | As an investor I want to learn how a stock market works | Investors can learn about how a stock market works
1-G | As an investor I want to learn about commodities so that I can have better understand them | Investors can learn about trading commodities
1-H | As an investor I want to learn about the common trading tactics so that I can come up with better investment strategies | Investors will be able to learn about the common trading tactics
1-I | As an investor I want to learn about the common trends in stock price graphs so that I can interpret what is happening in the graphs | Investors will be able to learn about the common stock price trends
1-J | As an investor I want to learn about the common investment strategies so that I can plan my investment strategies | Investors will be able to learn about the common investment strategies
1-K | As an investor, I want to learn about the things that influence the selection of an investment strategy | Investors will be able to learn about the things that impact the selection of a trading strategy
1-L | As an investor I want to learn about the tax implications of my investment strategy | Investors will be able to learn about the tax implications of their investment strategy
2 | As an investor I want to search for stocks so that I can see real time information about the stock | Investors can search for stocks and access real time graphs
2-A | As an investor I want to search for stocks so that I can find stock trading volume for a selected date | Investors can access volume trading information about a stock for a selected date range
2-B | As an investor I want to search for stocks so that I can find out about the market cap | Investors can access market cap information for a stock
2-C | As an investor I want to search for stocks so that I can find the share price about the stock | Investors can access share price infromation for a given stock
2-D | As an investor I want to search for stocks so that I can find real time graphs about the stock | Investors can access real time graphs
2-E | As an investor I want to search for stocks so that I can find the recent history of the stock | Investors can access the recent history of a stock
2-F | As an investor I want to search for stocks so that I can find the 52 week high/low | Investors can access the 52 week high/low of a stock
2-G | As an investor I want to search for stocks so that I can find the profit margin | Investors can access the profit margin of a stock
2-H | As an investor I want to search for stocks so that I can find the P/E ratio | Investors can access the P/E ratio of a stock
2-I | As an investor I want to search for stocks so that I can find the operating margin | Investors can access the operating margin of a stock
2-J | As an investor I want to search for stocks so that I can find the forward dividend & yield | Investors can access the forward dividend & yield of a stock
3 | As a content creator I would like to create content for investors to view | Content creators can create content that is viewable by investors
3-A | As a content creator I would like to create a learning series so that investors can learn about markets | Content creators can create a learning series for investors
3-B | As a content creator I would like to create a page so that investors can learn about markets | Content creators can create pages to educate investors
3-C | As a content creator I would like to be able to delete pages so that I can removed old pages | Content creators can delete pages
3-D | As a content creator I would like to edit existing series so that mistakes can be fixed | Content creators can edit existing pages
4 | As an investor I want to see financial news so that I can perform better as a investor | Investors can view relevant financial news
4-A | As an investor I want to read financial news articles so that I can learn more about companies | Investors can view relevant financial news articles for information
4-B | As an investor I want to read financial news so that I can know whats going on in the world currently | Investors can view current financial news
4-C | As an investor I would like to see news about a specific stock that i'm interested in | Investors will be able to view current financial news

## Product Backlog
Story # | Front Card | Back Card | Sprint Number | Priority | Assigned To | Comments | Estimated Points | Estimated Hours | Actual Hours | Hours | Points
ST1 | As an investor I want to access graphs of stock ticker data | Investors can access graphs of stock ticker data | 1 | 1 |  |  | 21 | 15 |  | 1 | 1
ST2 | As an investor I want to access the landing page | Investors can access the landing page | 1 | 2 |  |  | 21 | 15 |  | 1 | 1
ST3 | As an investor I want to search for stocks so that I can find the share price about the stock | Investors can access share price infromation for a given stock | 1 | 3 |  |  | 5 | 5 |  | 3 | 3
ST4 | As an investor I want to search for stocks so that I can find stock trading volume for a selected date | Investors can access volume trading information about a stock for a selected date range | 1 | 4 |  |  | 5 | 5 |  | 5 | 5
ST5 | As an investor I want to search for stocks so that I can find the recent history of the stock | Investors can access the recent history of a stock | 1 | 5 |  |  | 5 | 5 |  | 6 | 8
ST6 | As an investor I want to be able to access a page where I can learn about investing | Investors can access a learning page | 2 | 6 |  |  | 21 | 15 |  | 10 | 13
ST7 | As an investor I want to learn how to trade stocks so that I can buy/sell stocks | Investors can learn about trading stocks | 2 | 7 |  |  | 8 | 6 |  | 15 | 21
ST8 | As an investor I want to learn about what markets are | Investors can learn about what markets are | 2 | 8 |  |  | 8 | 6 |  | 20 | 32
ST9 | As an investor I want to learn about penny stocks so that I can make smarter decisions | Investors can learn about penny stocks | 2 | 9 |  |  | 8 | 6
ST10 | As an investor I want to learn about day trading so that I can day trade better | Investors can learn about day trading | 2 | 10 |  |  | 8 | 6
ST11 | As an investor I want to learn about long term stock investment so that I can perform better | Investors can learn about long term stock investment | 2 | 11 |  |  | 8 | 6
ST12 | As an investor I want to learn how a stock market works | Investors can learn about how a stock market works | 3 | 12 |  |  | 8 | 6
ST13 | As an investor I want to learn about commodities so that I can have better understand them | Investors can learn about trading commodities | 3 | 13 |  |  | 8 | 6
ST14 | As an investor I want to learn about the common trading tactics so that I can come up with better investment strategies | Investors will be able to learn about the common trading tactics | 3 | 14 |  |  | 8 | 6
ST15 | As an investor I want to learn about the common trends in stock price graphs so that I can interpret what is happening in the graphs | Investors will be able to learn about the common stock price trends | 3 | 15 |  |  | 8 | 6
ST16 | As an investor I want to learn about the common investment strategies so that I can plan my investment strategies | Investors will be able to learn about the common investment strategies | 3 | 16 |  |  | 8 | 6
ST17 | As an investor, I want to learn about the things that influence the selection of an investment strategy | Investors will be able to learn about the things that impact the selection of a trading strategy | 3 | 17 |  |  | 8 | 6
ST18 | As an investor I want to learn about the tax implications of my investment strategy | Investors will be able to learn about the tax implications of their investment strategy | 3 | 18 |  |  | 8 | 6
ST20 | As an investor I want to search for stocks so that I can find out about the market cap | Investors can access market cap information for a stock | 2 | 20 |  |  | 3 | 3
ST21 | As an investor I want to search for stocks so that I can find the 52 week high/low | Investors can access the 52 week high/low of a stock | 2 | 21 |  |  | 3 | 3
ST22 | As an investor I want to search for stocks so that I can find the profit margin | Investors can access the profit margin of a stock | 2 | 22 |  |  | 3 | 3
ST23 | As an investor I want to search for stocks so that I can find the P/E ratio | Investors can access the P/E ratio of a stock | 2 | 23 |  |  | 3 | 3
ST24 | As an investor I want to search for stocks so that I can find the operating margin | Investors can access the operating margin of a stock | 2 | 24 |  |  | 3 | 3
ST25 | As an investor I want to search for stocks so that I can find the forward dividend & yield | Investors can access the forward dividend & yield of a stock | 2 | 25 |  |  | 3 | 3
ST26 | As a content creator I would like to create a learning series so that investors can learn about markets | Content creators can create a learning series for investors | 4 | 26 |  |  | 13 | 10
ST27 | As a content creator I would like to create a page so that investors can learn about markets | Content creators can create pages to educate investors | 4 | 27 |  |  | 13 | 10
ST28 | As a content creator I would like to edit existing series so that mistakes can be fixed | Content creators can edit existing pages | 4 | 28 |  |  | 13 | 10
ST29 | As a content creator I would like to be able to delete pages so that I can removed old pages | Content creators can delete pages | 4 | 29 |  |  | 13 | 10
ST28 | As an investor I would like to be able to upgrade to the premium edition of Money Market | Investors can purchase premium | 3 | 19 |  |  | 13 | 10
ST29 | As an investor I would like to be able to view news stories | Investors can view news stories | 2 | 11 |  |  | 13 | 10

## Doing
Story # | Front Card | Back Card | Sprint Number | Priority | Assigned To | Comments | Estimated Points | Estimated Hours | Actual Hours | Hours | Points
ST2 | As an investor I want to access the landing page | Investors can access the landing page | 1 | 2 | Teh Peh |  | 21 | 15 | 13 | 1 | 1
ST6 | As an investor I want to learn how to trade stocks so that I can buy/sell stocks | Investors can learn about trading stocks | 3 | 6 |  |  | 8 | 6 | 5 | 15 | 21
ST7 | As an investor I want to learn about what markets are | Investors can learn about what markets are | 3 | 7 |  |  | 8 | 6 | 4 | 20 | 32
ST8 | As an investor I want to learn about penny stocks so that I can make smarter decisions | Investors can learn about penny stocks | 3 | 8 |  |  | 8 | 6 | 6
ST9 | As an investor I want to learn about day trading so that I can day trade better | Investors can learn about day trading | 3 | 9 |  |  | 8 | 6 | 6
ST10 | As an investor I want to learn about long term stock investment so that I can perform better | Investors can learn about long term stock investment | 3 | 10 |  |  | 8 | 6 | 6
ST11 | As an investor I want to learn how a stock market works | Investors can learn about how a stock market works | 3 | 11 |  |  | 8 | 6 | 6
ST12 | As an investor I want to learn about commodities so that I can have better understand them | Investors can learn about trading commodities | 3 | 12 |  |  | 8 | 6 | 6
ST13 | As an investor I want to learn about the common trading tactics so that I can come up with better investment strategies | Investors will be able to learn about the common trading tactics | 3 | 13 |  |  | 8 | 6 | 5
ST14 | As an investor I want to learn about the common trends in stock price graphs so that I can interpret what is happening in the graphs | Investors will be able to learn about the common stock price trends | 3 | 14 |  |  | 8 | 6 | 4
ST15 | As an investor I want to learn about the common investment strategies so that I can plan my investment strategies | Investors will be able to learn about the common investment strategies | 3 | 15 |  |  | 8 | 6 | 5
ST16 | As an investor, I want to learn about the things that influence the selection of an investment strategy | Investors will be able to learn about the things that impact the selection of a trading strategy | 3 | 16 |  |  | 8 | 6 | 5
ST17 | As an investor I want to learn about the tax implications of my investment strategy | Investors will be able to learn about the tax implications of their investment strategy | 3 | 17 |  |  | 8 | 6 | 5
ST28 | As an investor I would like to be able to upgrade to the premium edition of Money Market | Investors can purchase premium | 3 | 18 | Riley Jenkins |  | 13 | 10 | 11

## Done
Story # | Front Card | Back Card | Sprint Number | Priority | Assigned To | Comments | Estimated Points | Estimated Hours | Actual Hours | Hours | Points
ST1 | As an investor I want to access graphs of stock ticker data | Investors can access graphs of stock ticker data | 1 | 1 | Logan Johnston |  | 8 | 6 | 7 | 1 | 1
ST2 | As an investor I want to search for stocks so that I can find the share price about the stock | Investors can access share price infromation for a given stock | 1 | 2 | Austin Fraley |  | 5 | 5 | 5 | 3 | 3
ST3 | As an investor I want to search for stocks so that I can find stock trading volume for a selected date | Investors can access volume trading information about a stock for a selected date range | 1 | 3 | Austin Fraley |  | 5 | 5 | 5 | 5 | 5
ST4 | As an investor I want to search for stocks so that I can find the recent history of the stock | Investors can access the recent history of a stock | 1 | 4 | Austin Fraley |  | 5 | 5 | 5 | 6 | 8
ST18 | As an investor I want to search for stocks so that I can find out about the market cap | Investors can access market cap information for a stock | 2 | 18 | Austin Fraley |  | 3 | 3 | 3
ST19 | As an investor I want to search for stocks so that I can find the 52 week high/low | Investors can access the 52 week high/low of a stock | 2 | 19 | Austin Fraley |  | 3 | 3 | 3
ST20 | As an investor I want to search for stocks so that I can find the profit margin | Investors can access the profit margin of a stock | 2 | 20 | Austin Fraley |  | 3 | 3 | 3
ST21 | As an investor I want to search for stocks so that I can find the P/E ratio | Investors can access the P/E ratio of a stock | 2 | 21 | Austin Fraley |  | 3 | 3 | 2
ST22 | As an investor I want to search for stocks so that I can find the operating margin | Investors can access the operating margin of a stock | 2 | 22 | Austin Fraley |  | 3 | 3 | 2
ST23 | As an investor I want to search for stocks so that I can find the forward dividend & yield | Investors can access the forward dividend & yield of a stock | 2 | 23 | Austin Fraley |  | 3 | 3 | 2
ST29 | As an investor I would like to be able to view news stories | Investors can view news stories | 2 | 11 | Logan Johnston |  | 13 | 10 | 9